## Details
S.No. | Task | Status | Duration(Days)
1 | Home Internet Connection (Will be done within two days) (Mohtashim) | Done
2 | PayPal integration. We have to create account for the website in PayPal. (Danish)(Mohtashim). |  | 2
3 | Credit Card Service details. (Danish). Implementation. (Mohtashim) |  | 3
4 | Actual TAX calculation. (Danish). (Mohtashim). |  | 1
5 | Company’s bank details to be integrated to collect fees from vendors on transactions. (Danish) (Mohtashim) |  | 1
6 | Documentation and Learning videos for Vendors. (Mohtashim). | Done | 5
Note: Point # 2,3,5 Will be done parallel. Need details for point 2 and 3 ASAP.